## Slide 1: Work Plan - India
Iii pArtners’ Meeting
November 20, 2014
Neha Tomar & Shreya Kaushik
CUTS International

## Slide 2: Work Plan
Activity Types | Description | Time line | Activities vis-a-vis NAP | Operational Approach | Intended Output/Outcome
NRG IV |  | Jan – Feb, 2015 | Share work plan (Phase III) with NRG members | 1 – 2 press coverage | Finalisation of the work plan and initiation of stakeholder dialogue
Research & Dialogues | Pro/Anti competitive policies/practices and their impacts on consumers and producers | Jan – May, 2015 | Wheat - Quantifying impact of seed sector reforms on farmers in a district in Bihar - Analysing the impact of abolishment/ embracement of APMC - Reviewing the operational structure of PACS | - Firm up linkage of reforms & impacts from sec. & prim data - Undertaking extensive SH interactions to understand gaps/ good practices & take the work plan forward | Governments recognise the need for considering CREW findings

## Slide 3: Contd.
Activity Types | Description | Time line | Activities vis-a-vis NAP | Operational Approach | Intended Output/Outcome
Research & Dialogues | Pro/Anti competitive policies/practices and their impacts on consumers and producers | Jan – May, 2015 | Bus Transport - Impact of GSRTC (Gujarat) monopoly on other producers (entry barrier) - Reviewing the legal structure of AMTS - Need for a ‘State Public transport Regulator’ in MP - Review of new intended policy regime | - Interaction with senior civil servants/ govt, dpart. and private operators - Evidence based note (CN) from CREW findings - Comments on the draft Road Transport and Safety Bill | Governments recognise the need for considering CREW findings

## Slide 4: Contd.
Activity Types | Description | Time line | Activities vis-a-vis NAP | Operational Approach | Intended Output/Outcome
Important Meetings | Four rounds of Meetings with Parliamentarians and Policymakers Two government business fora | Jan – May, 2015 | Inter-state regulators meeting on good practices and regulations (one under each sector) | - Platform for knowledge exchange of interstate policy makers - Identification of one-two reforms to advocate and pursue with policy makers | Governments recognise the need for considering CREW findings

## Slide 5: Contd.
Activity Types | Description | Time line | Activities vis-a-vis NAP | Operational Approach | Intended Output/Outcome
NRG V |  | May – June, 2015 | Providing updates on progress of NAP and taking inputs | 1-2 press coverage | Validation of the NAP’s progress and outreach
Public Information dissemination | Media campaign to increase awareness & understanding about the impacts of competition reforms for consumers and producers | Jan – Aug, 2015 | Based on the experience and outcomes of activities mentioned above | - CREW calendar 2015 - Dialogue of project team with media personnel | Greater visibility of CREW findings

## Slide 6: Expected Impediments in NAP Application
Both agriculture and bus transport are in the state list, hence the uptake of methodology in other states maybe a challenge
Will to change outdated policies is limited
Beaurucratic structure not only in decision making but in simple interaction as well
Limited budgetary resources for project implementation

## Slide 7
Khop Kun Kra!!!