## Slide 1: National Advocacy Plan: Competition Reforms on Rice and Bus Transport
Madeiline Joy Aloria
Action for Economic Reforms
November 2014

## Slide 2: Recall
The main problems were identified:
  Rice Sector: Trade monopoly of the National Food Authority and the quantitative restriction
  Bus Transport: Traffic congestion and economic losses due to cut-throat competition of bus operators and perverse incentives

## Slide 3: Direction
Long Run:
  Rice
    Removing the monopoly of the NFA
    Removal of Import Quota (2017)
    Promoting a strategy for competitive rice sector beyond 2017
  Bus
    Reforming the LTFRB
    Legislation on re
Short Run
  Shaping Public Opinion: Enable the public connect the identified cause to the problem
  Broadening ownership of reform: coalition building
  Consolidating the core of reformers

## Slide 4: workplan
Activity Types | Activities Description (as per Proposal) | Duration | Country-Specific Activities based on National Advocacy Plan | Operational Approach | 
NRG - IV | Fourth Meeting of the NRG Members | January - Feb 2015 | Sharing of Workplan with NRG members; Gathering inputs and contacts for stakeholder mapping; | 1 - 2 press coverage | Finalization of work plan; Gathering initial inputs about stakeholders
Research | Mapping of 'influencers' or champions Journalist mapping and political mapping | January 2015 | Initial list: Proponents of anti-trust bills in the Philippines Partners in the government sector: Department of Trade and Investment (DTI), NEDA, etc Journalists | Preliminary mapping which is to be consulted with the team in the next NRG meeting. Specific activities will include: Brainstorming and scanning of profiles to know about their general stance on the issues) | Identification of the champions and opinion shapers
 | Pro/Anti competitive practices in two sectors and their impacts on consumers and producers. Competition distorting policies in the sectors | January - May 2015 | For the Philippines: Developing an interim strategy for 'promoting a competitive rice-market post 2017' and exploring fare-regulation in Metro Manila as a measure to regulate competition in the bus transport sector. | Close engagement with senior civil servants on the findings of the research. Making relevant government agencies and regulators a partner in the process | Governments recognize the need for considering CREW findings for relevant policy and/ or practice

## Slide 5: workplan
Activity Types | Activities Description (as per Proposal) | Duration | Country-Specific Activities based on National Advocacy Plan | Operational Approach | 
Coalition building and Public Information Dissemination | Influencing the “influencers” and the public | January - August 2015 | Preliminary: Issues for Media Campaign: (1) QR on rice in the Philippines, (2) Costs an causes of congestion due in EDSA | Emailing or faxing letters to influencers Columns to be published in identified partners: BusinessWorld (YellowPad) and Rappler, etc | Output: Media coverage/reports ¦ Outcome: Greater visibility of the CREW findings (policy reforms) resulting in bottom up pressure
Dialogue | Four rounds of meetings with policy makers to discuss and brainstorm on the findings | January - May 2015 | Philippines: Involving national entities that have experience of working with parliamentarians | Identification of 1 - 2 reform (policy and practice) that can be pursued with the government to consider for adoption. Identification of senior influencers (friends of competition) who can push the reform agenda | 
Dialogue | Two government business to identify the way forward for fair markets and resulting pro-industry benefits | January - May 2015 | Philippines: Dialogue on strengthening Association of Transport Service providers - 2 |  | 

## Slide 6: workplan
Activity Types | Activities Description (as per Proposal) | Duration | Country-Specific Activities based on National Advocacy Plan | Operational Approach | 
Research | Mapping of stakeholders in the bus and the rice sectors | January to May 2015 | For bus, special focus on established transport groups as well as commuters often using the EDSA super-corridor; For rice, players in the chain will also be mapped, as well as relevant government agencies. Initial list of stakeholders to map for the bus sector: Transport groups and operators Representatives from other means of transportation Government/ Regulators MMDA, LTFRB, LTO, etc Non-transport entities Students Employees Ordinary commuters Initial list of stakeholders to map for the rice sector: National Food Authority and National Food Authority Employees Association Applicants for retail, wholesale, mill, warehouse, etc. Licensed retailers, wholesalers, millers, other players, and their dependents (workers) Organized farm or rice groups Relevant government agencies such as Department of Agriculture International Rice Research Institute, Philippine Rice Research Institute Lending institutions Pro-farmers group and agriculture-related civil society organizations | Analyzing through media articles the characteristics and stance of the stakeholders regarding the issue at hand. | A document presenting a matrix of stakeholders, their profiles, recent actions undertaken, political background if applicable, etc.

## Slide 7: workplan
Activity Types | Activities Description (as per Proposal) | Duration | Country-Specific Activities based on National Advocacy Plan | Operational Approach | 
Research and brain storming | Menu of policy options | March, 2015 | Menu of policy options which will present each option based on technical merit and political feasibility. | Through brainstorming and research: Coming up with a matrix of policy options. The inputs are from various research. It will assess each policy option based on feasibility, etc | 
Dialogue | Opinion Solicitation Focus Group Discussion | March, 2015 | "What is the most preferred reform choice among the stakeholders? Which may be done in the short run" We already presume answers from stakeholders such as the bus sector and the NFA employees association (of course, opposition to the reform), but for other stakeholders, their ideas have yet to be solidified. | A series of sectoral focus group discussions involving the stakeholders. Proposed FGDs are separate for each category of stakeholder: commuters, transport groups, etc | Validated stakeholder map; Summary of FGD answers and a matrix of "votes" or insights on the preferences of the stakeholders regarding the menu of policy options.

## Slide 8: workplan
Activity Types | Activities Description (as per Proposal) | Duration | Country-Specific Activities based on National Advocacy Plan | Operational Approach | 
Research and Brainstorming | Re-developing a communication plan and formulation of the key messages: | March 2015 | After the sets of research on media options and discussions on what is the most preferred outcome or policy/practice change by the stakeholders, a communication plan is to be developed. This would specify the messaging of packaging of the reform. | Research | 
NRG - V | Fifth Meeting of the NRG | May - June 2015 |  | 1 - 2 press coverage | 
Capacity Building | 2 National orientation workshops on the FCPs (for national policy makers, business chambers, regulators, civil society) in each country | May - August 2015 |  | Explore partnership with competition agency, business chambers, think-tanks, development partners | Capacitating allies and building networks
NRG - VI | Sixth meeting of the NRG | July - August 2015 |  | 1- 2 media reports | 

## Slide 9: workplan
Activity Types | Activities Description (as per Proposal) | Duration | Country-Specific Activities based on National Advocacy Plan | Operational Approach | 
Additional Activities | Certain additional advocacy activities would be undertaken depending on the situation on the ground in countries to build up pressure for governments to build up momentum for countries to adopt aproaches for promoting competition and incorporating a M&E system to compute impact on beneficiaries | January - August 2015 | Advocacy in other sectors in the countries (with regulators, development partners) for up-take in them, etc |  | Enhance the popularity of the CREW beyond pilot countries