## Slide 1: WORK PLAN- ZAMBIA
III Partners Meeting
November 20, 2014
By: Faith Mwamba

## Slide 2: Work Plan
Activity Types | Activities Description (as per Proposal) | Time Period (Duration) | Country-Specific Activities based on National Advocacy Plan | Operational Approach | Intended Output/Outcome (CREW LOGFRAME)
NRG-IV | Fourth Meeting of the NRG Members | Jan/Feb 2015 | Share the Work-Plan (Phase-3) with NRG members for their guidance and inputs | 1-2 press coverage | 
Research | Pro/Anti-competitive practices in two sectors and their impacts on consumers and producers (to be done in partnership with the respective competition agency in the project countries) | Jan-May 2015 | Maize Study which defines the international best practices on pricing capturing examples from other countries Quantifying the impact of abolition of ‘subsidies’ on maize millers ( whether we can attribute increase in prices to removal of subsidies or other factors) Indexing of farmers and identifying of beneficiaries and non-beneficiaries of FRA | - Engagement with senior govt, and constitutional office holders on the findings of the research to identify points of entry for influencing policy change -Issue a discussion papers on the benefit of reforms | Governments recognise the need for considering CREW findings (suggested reforms) for relevant policy and/or practice

## Slide 3: CONTD..
 |  |  | Bus Transport Conducting a regional analysis on price setting mechanisms Assessing the efficacy of route rationalisation Reviewing the regulatory framework and institutional settings of RTSA | -Exchange ideas with policy makers and implementers on best practices of fare revision. -Initiate debate on key identified areas of reform and advocate for appropriate policy implementation | 

## Slide 4: CONTD..
Dialogues | Meetings with Parliamentarians and Policymakers (to discuss and brainstorm on the findings) | Jan-May 2015 | Discussion on reviewing the ‘fare setting ( Pricing)’ process in bus transport in Zambia Lobbying for implementation of input vouchers to improve access for small scale farmers Discussion on ‘route rationalisation’ in bus transport sector Lobbying for a more transparent procurement process that will include more players Better coordination and cooperation between RTSA and Ministry of Transport through dialogue | -Engage with govt, RTSA and SH and share best practices on fare setting -engage with constitutional office holders and pursue implementation of policy -Initiate dialogue with key SH and champions in the Maize sector (CCPC and ZPPA) And pursue policy change -Undertaking extensive SH interactions to understand the gaps and better policy implementation outcomes | Governments recognise the need for considering CREW findings (suggested reforms) for relevant policy and/or practice

## Slide 5: Contd.
NRG-V | Fifth Meeting of the NRG | May-June, 2015 |  | 1-2 press coverage (countries) | 
Public information dissemination | Media campaign to increase awareness and understanding about the positive impacts of competition reforms for consumers and producers | Jan – Aug, 2015 | Initiate evidence based debate among SH and Market players on the findings and experiences from the study | -Interviews of researchers and sector specific SH on Media Platforms -Media Articles (policy briefs, briefing papers etc) -Press briefings on specific sector issues arising from the study -Conducting educational plays on the benefits of competition reforms (coupled with Information brochures) | Greater visibility of the CREW findings (policy reforms) resulting in bottom-up pressure

## Slide 6: Possible Challenges
The political economy surrounding both sectors would be a challenge in implementing some activities
Long procedures within the institutional systems
Long legislative process for efficient policy implementation

## Slide 7
ENDS…